## Sprint1
Week 1 (25th Feb - 3rd Mar)
WEEKLY SCRUM REPORT
Scrum Master: Kanupriya Sanjay Agrawal
Team Member Name | Tasks worked | Tasks going to work on | Blockers
Kanupriya Sanjay Agrawal | Discussed on things related to Sprint Tennure, Meetings, Planning | Design Scrum artifacts, decide on scrum meetings, integrate Jira | None
Kusuma Padma Kavya Bandi | Understanding the project requirement and analysis | Design Google Task Sprint sheet, explore different technologies | None
Nikhil Konduru | Communicated various PROS/CONS of each technology to be used | Research tech stack and finalise one | None
Rishab Reddy Karakala | Discussed task allocation and requirement analysis | Task allocation and research on which cloud provider to be used | None
XP CORE VALUE REPORT
Core Values | How we maintained
1. Feedback | Taking everyone's feedback on role-based actions.
2. Communication | Scheduled meeting on Monday, Wednesday and Friday to discuss the sprint.
3. Respect | Respected everyone's ideas and opinions about tech stack